## Sheet1
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
[6 empty] | KW47 |  |  |  |  | KW48 |  |  |  |  | KW49 |  |  |  |  | KW50 |  |  |  |  | KW51 |  |  |  |  | KW52 |  |  |  |  | KW1 |  |  |  |  | KW2 |  |  |  |  | KW3 |  |  |  |  | KW4 |  |  |  |  | KW5 |  |  |  |  | KW6
|  |  |  | Overdue |  | 1: 20.11.2023; 6: 27.11.2023; 11: 04.12.2023; 16: 11.12.2023; 21: 18.12.2023; 26: 25.12.2025; 31: 01.01.2024; 36: 08.01.2024; 41: 15.01.2024; 46: 22.01.2024; 51: 29.01.2024; 56: 05.20.2024
Nr | Tasks | Responsible | end | days | status | mo | tu | we | th | fr | mo | tu | we | th | fr | mo | tu | we | th | fr | mo | tu | we | th | fr | mo | tu | we | th | fr | mo | tu | we | th | fr | mo | tu | we | th | fr | mo | tu | we | th | fr | mo | tu | we | th | fr | mo | tu | we | th | fr | mo | tu | we | th | fr | mo | tu | we | th | fr | In progress
1 | Scan's overview document with correction rate of the scanns | Natalia | 2023-12-23 | 26 | done | [60 empty] | done | bar: 27.11.2023 mo to 04.12.2023 fr
2 | Setup OBR computer (local account) | Denis & Lukas | 2024-01-15 | 3 | done | [60 empty] | not started | bar: 11.12.2023 mo to 18.12.2023 fr; 01.01.2024 fr to 08.01.2024 fr
3 | Flatening panel solution (antireflection) | Marcos | 2024-01-12 | 6 | done | bar: 04.12.2023 mo to 04.12.2023 fr
4 | Problem and progression table | Denis | 2023-12-15 | 34 | done | bar: 04.12.2023 mo to 11.12.2023 fr
5 | Skript to automatize the conversion and get scanner ready | Lukas | 2024-01-12 | 6 | done | bar: 04.12.2023 mo to 04.12.2023 we; 08.01.2024 mo to 08.01.2024 tu
6 | 3d printed slope | Denis | 2023-12-23 | 26 | done | bar: 18.12.2023 mo to 18.12.2023 fr
7 | Guidace / Scanner Manual | Natalia & Lukas | 2024-01-15 | 3 | done | bar: 08.01.2024 mo to 15.01.2024 we
8 | Frame to help book placement | Marcos | 2024-01-12 | 6 | done | bar: 08.01.2024 mo to 15.01.2024 we
9 | GitHub Repository | Lukas & Denis | 2024-01-17 | 1 | done | bar: 08.01.2024 mo to 08.01.2024 fr
10 | Creating presentation (pp) 18th january | Everybody | 2024-01-17 | 1 | done | bar: 15.01.2024 mo to 15.01.2024 we
11 |  |  |  | 45309
12 |  |  |  | 45309
13 |  |  |  | 45309
14 |  |  |  | 45309
15 |  |  |  | 45309
16 |  |  |  | 45309
17 |  |  |  | 45309
18 |  |  |  | 45309
19 |  |  |  | 45309
20 |  |  |  | 45309
21 |  |  |  | 45309
22 |  |  |  | 45309
23 |  |  |  | 45309
24 |  |  |  | 45309
25 |  |  |  | 45309
26 |  |  |  | 45309
27 |  |  |  | 45309
28 |  |  |  | 45309
29 |  |  |  | 45309
30 |  |  |  | 45309
Formulas:
days = TODAY()-[end]

## Questions
1 | Should we be able to scan all kind of Books? Should we prioritize one specific type?
2 | How you prefer the process to be? Everybody is going to use the system, or just "trained" people? (automatic skript)
3 | Which sw is used from you?
4
pc used just for scanning
1 we should be able to scan all types of books, but more important is to have a document that tells the correction rate of every type of book
2 have frames to help to the process
3 have a way to set up the scanner lights settings just pressing one button (maybe with audio)
4 output file always in same folder and person can rename it
5 write in the manual what the persons have to do
6 get familiar with screenreader ctrl windows enter (narrator)